## Sheet1
Preliminary Master Schedule for the 2024 Bond Projects - Columbus Independent School District
PBK Architects, Inc.
September 2024 (Revised)
Project Name | Total Project Cost | Construction Budget | Soft Costs | April 2024 |  | May 2024 |  | June 2024 | July 2024 | Aug 2024 | Sept 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | June 2025 | July 2025 | Aug 2025 | Sept 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | April 2026 | May 2026 | June 2026 | July 2026 | Aug 2026 | Sept 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027
Hiring the |  |  |  |  | May Bond Referendum
Construction Manager/Risk
Board of Trustees selects Construction manager at Risk
as the Delivery Method at their Regular Meeting in July 2024
.
[9 empty] | RFQ for CM@Risk |  |  |  | .
.
.
[8 empty] | June 10th, Board of Trustees |  |  |  |  | ..
Selects the Delivery Method at their regular Board meeting
Board of Trustees Canvases the Votes
at their Regular Meeting on May 15th.
Bond Oversite Committee Meetings
Meetings
New CTE Building
[8 empty] | Schematic Design |  |  |  |  | Presentation to the Board of Trustees |  |  | Release Documents for Competitive
[13 empty] | for Approval of Design Development |  |  | Bidding to Interested Subcontractors
at their meeting on November 11, 2024
Design Development
75% Construction Documents
Review with Columbus ISD
[13 empty] | Construction Documents |  |  |  |  | Board of Trustees accepts amendment to the Contract
with the Construction Manager for the GMP at their
meeting in April 2025
Bidding
[12 empty] | Estimate due from Drymalla | [15 empty] | Substantial Completion
[12 empty] | Construction on September 20, 2024 | [6 empty] | Construction Phase
[28 empty] | Warranty Period Begins | [9 empty] | 11 Month Walk-Through in December 2026
25% Construction Documents
[14 empty] | Internal Review | [25 empty] | End of Warranty Period
| 5255542 | 4379620 | [13 empty] | Negotiations and Permitting
Professional Fees(6%) |  |  | 262777 | [10 empty] | 50% Construction Documents
Geotech Reports/Surveys/Material Testing(2%) |  |  | 87592 | [10 empty] | Internal Review | [10 empty] | Furniture Purchase and Installation
Furniture(7%) |  |  | 306576
Technology(5%) |  |  | 218980
PBK Project Number 17375
New Elementary School
Addition/Renovation
[13 empty] | Presentation to the Board of Trustees |  |  | Release Documents for Competitive
[8 empty] | Schematic Design |  |  |  |  | for Approval of Design Development |  |  | Bidding to Interested Subcontractors
at their meeting on November 11, 2024
[10 empty] | Design Development |  |  |  |  | 75% Construction Documents
[15 empty] | Review with Columbus ISD |  |  | Board of Trustees accepts amendment to the Contract
[13 empty] | Construction Documents |  |  |  |  | with the Construction Manager for the GMP at their
meeting in April 2025
[12 empty] | Estimate due from Drymalla |  |  |  | Bidding
Construction on September 20, 2024
[19 empty] | Construction Phase for New Addition | [12 empty] | Substantial Completion
25% Construction Documents
[14 empty] | Internal Review | [14 empty] | Renovations to the existing Building
Negotiations and Permitting
[14 empty] | 50% Construction Documents | [17 empty] | Warranty Period Begins | [9 empty] | 11 Month Walk-through in April 2027
| 8347008 | 6955840 | [11 empty] | Internal Review
Professional Fees(6%) |  |  | 417350 | [38 empty] | End of Warranty Period
Geotech Reports/Surveys/Material Testing(2%) |  |  | 139117 | [25 empty] | Furniture Purchase and Installation
Furniture(7%) |  |  | 486908
Technology(5%) |  |  | 347790
PBK Project Number 17373
| 13602550 | 11335460 | 2267090 | April 2024 |  | May 2024 |  | June 2024 | July 2024 | Aug 2024 | Sept 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | June 2025 | July 2025 | Aug 2025 | Sept 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | April 2026 | May 2026 | June 2026 | July 2026 | Aug 2026 | Sept 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027
| Monthly Expenditures | Grand Total | 13602550 |  |  | Monthly Totals |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0